## Data Points & Integration
OmniBlend — Data Points & Integration Requirements ¦ Aligned with Implementation Lifecycle v1.0 ¦ Updated March 2026
Module or Category | Data Point | Current / Previous State - indicative | Real Data Source Required | Integration Method or Logic | Phase | Priority | Status | Lifecycle Reference
COMMAND DASHBOARD
Command Dashboard | Production Volume (L/day) | Simulated batch progress | MES/ERP completed batch volumes per production order | Pull completed batch volumes from MES production order records; sync on order close | P5 | HIGH | Simulated | §6 — MES/ERP Sync
Command Dashboard | Cost per Batch (£/L) | Random £1.75–£2.20 per tick | Actual material consumption × live supplier prices + energy kWh × tariff + packaging | Calculate at batch close from actual consumed quantities and live pricing feed (P6); display on dashboard | P5/P6 | HIGH | Simulated | §6, §7 — MES Sync + Supplier Pricing
Command Dashboard | Energy Usage (kWh) | 45 kWh × batch count (hardcoded) | Smart meter API per blender/pump (Building Management System) | Direct ingestion from BMS APIs into time-series DB; sum per batch window | P8 | STANDARD | Hardcoded | §9 — Go-Live / Observability
Command Dashboard | Equipment Utilisation % | Simulated — no real OT data | SCADA: actual run hours and downtime logs from DCS/PLC | Process SCADA run/stop status tags via OPC-UA bridge; calculate uptime % per equipment | P8 | STANDARD | Simulated | §9 — Go-Live / Observability
Command Dashboard | On-Spec Rate % | % batches with no UI alerts (not from lab) | LIMS: actual test pass/fail disposition per batch | Track LIMS pass/fail result per batch_id; calculate rolling On-Spec Rate % on dashboard | P4 | CRITICAL | Simulated | §5.2 Act.8 — LIMS Integration
Command Dashboard | Live Event Feed | 3% stochastic alert per tick | Real SCADA alarms, LIMS lab alerts, and MES/ERP system events | Webhooks from SCADA alarm forwarder (P3), LIMS connector (P4), and MES adapter (P5) → POST /api/v1/ingest/events/ | P3 | CRITICAL | Simulated | §4.2 Act.8 — SCADA Bridge
Command Dashboard | Energy Heatmap | Random values with shift multiplier | Smart meter time-series per equipment — 24 readings/device/day from BMS | Ingest 24 readings per device per day into TimescaleDB hypertable; render as hourly heat grid per device | P8 | STANDARD | Simulated | §9.1 Act.2 — Go-Live / Observability
Command Dashboard | Timeline | Simulated stage timestamps | MES production order status history — Released → Started → Confirmed with timestamps | Sync production order status transitions from MES into OmniBlend batch timeline on each status change | P5 | HIGH | Simulated | §6.2 Act.6 — MES/ERP Sync
BLEND SIMULATOR
Blend Simulator | Batch Stage | 2% progress per tick (time-based) | SCADA: DCS/PLC discrete signals at stage transitions (Weighing → Blending → Heating → QC → Complete) | Poll PLC stage-complete tags via OPC-UA bridge every 30–60 seconds; map to UI stage indicator | P3 | CRITICAL | Simulated | §4.2 Act.7 — SCADA Bridge
Blend Simulator | Blend Temperature (°C) | Drifts +0.3°C per simulation tick | Blender thermocouple PV reading via SCADA (OPC-UA/Modbus tag) | Ingest live thermocouple PV via SCADA bridge; display real-time value in Blend Simulator panel | P3 | CRITICAL | Simulated | §4.2 Act.5 — SCADA Bridge
Blend Simulator | Mixing Speed (RPM) | User-set value — no VFD feedback | Variable Frequency Drive (VFD) feedback reading from SCADA OPC-UA tag | Capture actual VFD feedback RPM via SCADA bridge; display alongside user setpoint for comparison | P3 | CRITICAL | Simulated | §4.2 Act.5 — SCADA Bridge
Blend Simulator | Progress % | Time-estimate only | Batch weighing system: dosing-complete signals per component from PLC | Calculate Progress % from actual weighed components and dosing-complete discrete signals via OPC-UA | P3 | CRITICAL | Simulated | §4.2 Act.7 — SCADA Bridge
Blend Simulator | Batch Volume (L) | Fixed at recipe target volume | Flow totaliser PV or batch weighing system actual accumulated reading | Real-time volume totalisation from flow meter PV tags or scale totaliser via SCADA bridge | P3 | CRITICAL | Simulated | §4.2 Act.6 — SCADA Bridge
Blend Simulator | Pipeline Flow | Visual animation only — no live data | Flow meter PV readings from SCADA for each pipeline segment | Translate live flow meter PV readings into UI animation speed/direction via OPC-UA bridge | P3 | CRITICAL | Simulated | §4.2 Act.6 — SCADA Bridge
TANK DIGITAL TWIN
Tank Digital Twin | Fill Level % (×12 Tanks) | Gaussian noise drift — no real sensor | Ultrasonic/radar level transmitter → SCADA → OPC-UA API (one per tank; 12 total) | Post transmitter PV data to /api/v1/ingest/ every 30–60 seconds via OPC-UA bridge; display on Tank DT | P3 | CRITICAL | Simulated | §4.2 Act.3 — SCADA Bridge
Tank Digital Twin | Temperature °C (×12 Tanks) | Slow drift with Gaussian noise | Thermocouple or RTD per tank → SCADA → OPC-UA API (one per tank; 12 total) | Real-time ingestion of tank temperature sensor PV via OPC-UA bridge; display on Tank DT | P3 | CRITICAL | Simulated | §4.2 Act.4 — SCADA Bridge
Tank Digital Twin | Status (Normal/Low/Critical) | Threshold on simulated fill level | SCADA LLL (Low-Low-Low) and LL alarm discrete tags forwarded to event API | Forward discrete SCADA alarm states from OPC-UA bridge to /api/v1/ingest/events/ event feed | P3 | CRITICAL | Simulated | §4.2 Act.8 — SCADA Bridge
Tank Digital Twin | Tank Capacity (L) | Hardcoded in application code | Physical tank datasheets (one-time configuration from P&ID and engineering drawings) | One-time configuration entry in system settings; linked to P&ID drawing reference in instrument register | P1 | CONFIG | Hardcoded | §2 — Infrastructure Foundation
Tank Digital Twin | Material Type | Hardcoded per tank | Tank management system or operator entry linked to MES production order | Integrate with MES tank-assignment data; allow operator override with audit trail | P5 | HIGH | Hardcoded | §6 — MES/ERP Sync
RECIPE LAB
Recipe Lab | Recipe Formulations | 10 hardcoded seed recipes (G40, A40, H20W50, R50, 2T + variants) | MES/ERP: active product formulations and historical product codes from SAP PP-PI master recipe | Sync active product formulations from ERP master recipe via RFC/BAPI or OData; version-control in OmniBlend | P5 | HIGH | Hardcoded | §6.2 Act.3 — MES/ERP Sync
Recipe Lab | Predicted Viscosity (KV40/KV100) | Linear regression on synthetic data (not from real LIMS) | Historical ingredient blends + actual LIMS viscosity results (200+ batches minimum) | Train ML GradientBoosting/Refutas model on real LIMS data (P4 archive); R² > 0.92 gate before deployment | P7 | HIGH | Simulated | §8.1 — ML Model Specifications
Recipe Lab | Predicted Flash Point | Formula-based (not from real LIMS) | Historical ingredient blends + actual LIMS flash point results (ASTM D92) — 200+ batches | Train Neural Network (2-layer, 64 nodes, ReLU) on real LIMS data; include tank history feature; R² > 0.92 gate | P7 | HIGH | Simulated | §8.1 — ML Model Specifications
Recipe Lab | Predicted TBN | Formula-based (not from real LIMS) | Historical ingredient blends + actual LIMS TBN results (ASTM D2896) — 200+ batches | Train RandomForest Regressor on additive concentration features; R² > 0.92 gate before deployment | P7 | HIGH | Simulated | §8.1 — ML Model Specifications
Recipe Lab | Cost per Litre (£/L) | Hardcoded unit costs — not from supplier | Live supplier pricing feed: EDI price lists or supplier portal REST API per raw material | Connect to EDI price lists or supplier portal APIs; scheduled daily ingestion with change detection and audit trail | P6 | HIGH | Hardcoded | §7 — Supplier Pricing Feed
Recipe Lab | AI Recipe Suggestions | Random candidate scoring — not optimised | Constrained optimisation (SciPy SLSQP) on real cost (P6) and quality objective functions (P7 models) | Run SciPy constrained optimisation: minimise £/L subject to viscosity ± tolerance, flash point ≥ min, TBN in range, sum = 100% | P7 | HIGH | Simulated | §8.2 Act.8 — ML Pipeline
QUALITY AI ENGINE
Quality AI Engine | Live Viscosity Readings | Formula-predicted (not from lab) | Online viscometer → SCADA → API, or manual LIMS entry from bench instrument (ASTM D445) | Ingest via SCADA bridge (online viscometer) or LIMS POST webhook (bench result); display actual vs predicted | P4 | CRITICAL | Simulated | §5.1 — LIMS Quality Parameters
Quality AI Engine | Live Flash Point Readings | Formula-predicted (not from lab) | Pensky-Martens or Cleveland OC instrument results → LIMS → POST /api/v1/quality/lab-results | Ingest actual lab test results via LIMS webhook triggered on analyst sign-off; target ≤5 min latency | P4 | CRITICAL | Simulated | §5.1 — LIMS Quality Parameters
Quality AI Engine | Live TBN Readings | Formula-predicted (not from lab) | Titration instrument results → LIMS → POST /api/v1/quality/lab-results (ASTM D2896) | Ingest actual titration results via LIMS webhook on analyst sign-off; align by batch_id and sample_time | P4 | CRITICAL | Simulated | §5.1 — LIMS Quality Parameters
Quality AI Engine | Predicted vs Actual Delta Panel | NOT BUILT — no comparison panel exists | LIMS actual results (P4) vs ML model predictions (P7) per batch | Activate Predicted vs Actual comparison panel in Quality AI Engine; display delta per parameter per batch; drives CI calculation | P4 | CRITICAL | Not built | §5.2 Act.3 — LIMS Integration
Quality AI Engine | Off-Spec Risk Meter | Formula penalties on range (hardcoded thresholds) | Statistical classifier trained on 500+ real batches with LIMS pass/fail labels | Train XGBoost classifier on combined process + quality features with LIMS labels; FN-rate < 5% gate | P7 | HIGH | Simulated | §8.1 — ML Model Specifications
Quality AI Engine | Confidence Intervals | Fixed ±5% (hardcoded — not from model performance) | Real ML model confidence derived from prediction vs actual deltas across historical batches | Bootstrap CI from model residuals (prediction vs LIMS actuals); replace fixed ±5% with dynamic per-model CI | P7 | HIGH | Hardcoded | §8.1 — ML Model Specifications
Quality AI Engine | Off-Spec Alert → Batch Hold | NOT BUILT — no hold notification | LIMS pass/fail disposition triggers automated batch hold notification to operator | Configure: LIMS fail → POST /api/v1/ingest/events/ with hold flag → operator acknowledgement required before release | P4 | CRITICAL | Not built | §5.2 Act.6 — LIMS Integration
Quality AI Engine | LIMS Archive for ML Training | NOT BUILT — no structured LIMS archive | Structured LIMS results aligned by batch_id and timestamp; minimum 200 batches for training P7 models | Configure LIMS result archiving in PostgreSQL table with all fields needed for ML feature engineering; begin accumulation Week 8 | P4 | CRITICAL | Not built | §5.2 Act.7 — LIMS Integration
Quality AI Engine | ML Drift Monitoring | NOT BUILT — no drift monitoring | Weekly MAE between model predictions and LIMS actuals per deployed model | Build ML drift monitoring dashboard; trigger retraining when MAE exceeds 1.5× validation MAE; display per model per week | P8 | STANDARD | Not built | §9.1 Act.7 — Go-Live / Observability
SUPPLY & COST OPTIMIZER
Supply & Cost Optimizer | Price per Litre (£/L) | Hardcoded static values — not from supplier | EDI price lists, supplier portal API, or ERP contract price table per material per supplier | Integrate with EDI price list feeds or supplier REST APIs; daily ingestion with effective date and expiry date tracking | P6 | HIGH | Hardcoded | §7.1 — Supplier Pricing Feed
Supply & Cost Optimizer | Lead Time (days) | Hardcoded 2–14 days (not from ERP) | ERP: historical PO-to-delivery performance from SAP MM (ME2M or equivalent) | Extract average lead time per supplier per material from ERP procurement history; replace hardcoded values | P6 | HIGH | Hardcoded | §7.1 Act.4 — Supplier Pricing Feed
Supply & Cost Optimizer | Quality Grade (A/B/C) | Hardcoded — not from incoming QC | Incoming raw material QC inspection results from LIMS (ASTM methods per material spec) | Link incoming raw material LIMS test results to Quality Grade A/B/C in Supply Optimizer; auto-update on new QC result | P4 | CRITICAL | Hardcoded | §5.2 Act.5 — LIMS Integration
Supply & Cost Optimizer | Reliability Score | Hardcoded 0.75–0.99 (not from ERP) | ERP: historical on-time delivery rate per supplier over rolling 12-month window | Calculate: on-time deliveries / total deliveries per supplier from ERP; recalculate monthly; replace hardcoded values | P6 | HIGH | Hardcoded | §7.1 Act.5 — Supplier Pricing Feed
AI CONTROL PANEL
AI Control Panel | Natural Language Commands | Regex/keyword pattern matching — no real NLP | Claude API (Anthropic REST API, api.anthropic.com) for real intent parsing | Route Claude API intent parsing to real internal API endpoints; implement request caching, fallback to keyword routing on timeout | P8 | STANDARD | Simulated | §9.1 Act.3 — Go-Live / Observability
DOCUMENT ASSISTANT (D0–D6 RAG)
Document Assistant | RAG Document Search (7 Knowledge-Base Docs: D0–D6) | Fully built — Ollama LLM + sentence-transformer embeddings; 7 documents chunked and indexed in vector store; real-time RAG pipeline operational | Internal document corpus: D0 (RAG Demo Guide, 88 prompts), D1 (Batch Mfg Record), D2 (SCADA Tag Register), D3 (Cybersecurity Risk Assessment), D4 (As-Is/To-Be Process Map), D5 (QC Procedures & Specs), D6 (LIMS Requirements Spec) | Vector similarity search: query → embedding → cosine similarity → top-K passage retrieval → Ollama LLM synthesis → structured response with source attribution; POST /api/v1/ai/doc-query | — | BUILT | Built (Simulator) | §0 — Simulator Shell (Extra Module — not in lifecycle plan)
Document Assistant | Quick Prompts Library (44 pre-loaded prompts, D0–D6) | Fully built — 44 prompts curated across D0–D6; grouped by document in tabbed interface; covers LOBP operations, SCADA, QC, cybersecurity, LIMS, process mapping | Internal — curated prompt library per knowledge-base document; no external data source required | Pre-configured query buttons trigger document-specific RAG pipeline; tab UI groups prompts by D0–D6 source document; results include passage provenance | — | BUILT | Built (Simulator) | §0 — Simulator Shell (Extra Module — not in lifecycle plan)
Document Assistant | AI Response with Source Attribution & Typing Effect | Fully built — AI responses rendered with real-time typing animation; cited source documents listed per response with document title and section references | Internal — Ollama LLM synthesis from retrieved passages; source document metadata (title, section) embedded in each response | RAG pipeline output structured with source passage metadata; frontend renders citations as named document cards alongside the streamed response text | — | BUILT | Built (Simulator) | §0 — Simulator Shell (Extra Module — not in lifecycle plan)
Document Assistant | Knowledge Base Status Tracker (Per-Document Load & Embedding Status) | Fully built — real-time status panel shows embedding load status and chunk count per document (D0–D6); visible in Document Assistant UI | Internal — document chunking and embedding pipeline; per-document status tracked in backend state; no external integration required | GET /api/v1/ai/doc-status returns per-document chunk count and embedding status; frontend renders as a live status dashboard with pass/fail indicators per document | — | BUILT | Built (Simulator) | §0 — Simulator Shell (Extra Module — not in lifecycle plan)
SAP ERP (ADDITIONAL)
SAP — QM Module | Inspection Lot ↔ OmniBlend LIMS | NOT BUILT — no QM integration | SAP QM inspection lots linked to OmniBlend LIMS pass/fail results; usage decision triggers goods issue | BAPI_QMEL_CREATE and QM OData API; pass/fail in OmniBlend drives QM usage decision enabling or blocking goods issue | P5 | HIGH | Not built | §6.1 — SAP Module Integration Matrix
SAP — PM Module | Equipment Master → Instrument Register | NOT BUILT — no PM integration | SAP PM equipment master data and maintenance notification history | Import equipment master (BAPI_EQUI_GETLIST / IE03 OData) to populate OmniBlend instrument registers and maintenance calendars | P5 | HIGH | Not built | §6.1 — SAP Module Integration Matrix
SAP — SD Module | Customer Quality Specs → Batch Plan | NOT BUILT — no SD integration | Customer-specific quality specifications from SAP SD sales orders | Pull customer quality specs from SD sales order (BAPI_SALESORDER_GETLIST) and load into batch quality plan | P5 | HIGH | Not built | §6.1 — SAP Module Integration Matrix
SAP — PP-PI Module | Material Consumption Postback | NOT BUILT — actuals not written back | Actual material quantities consumed per batch written back to SAP PP-PI for cost settlement | Post actuals (material number, planned qty, actual qty, UoM) to PP-PI via CO11N BAPI on batch close | P5 | HIGH | Not built | §6.2 Act.5 — MES/ERP Sync
PLATFORM & INFRASTRUCTURE
Platform | SCADA Bridge Heartbeat Monitor | NOT BUILT — no watchdog monitoring | 30–60 second polling cycle with bridge uptime target >99.5% over 7-day acceptance window | Implement watchdog monitor; alert on 3 consecutive missed heartbeats; log bridge uptime in observability platform | P3 | CRITICAL | Not built | §4.2 Act.9 — SCADA Bridge
Platform | APM / Application Monitoring | NOT BUILT — no observability layer | API latency (p50/p95/p99), error rates, WebSocket lag, PostgreSQL query times, Redis pub/sub rate | Deploy Datadog, Prometheus+Grafana, or equivalent; monitor all API endpoints and integration connectors | P8 | STANDARD | Not built | §9.1 Act.4 — Go-Live / Observability
Platform | Log Aggregation | NOT BUILT — no centralised log management | Application errors, security audit trail, SCADA bridge connectivity, LIMS connector activity, SAP errors | Deploy ELK Stack or AWS CloudWatch; configure log ingestion for all service types and integration systems | P8 | STANDARD | Not built | §9.1 Act.5 — Go-Live / Observability
Platform | On-Call / Alerting | NOT BUILT — no alerting configuration | PagerDuty or OpsGenie; API health, PostgreSQL, Redis, SCADA heartbeat, LIMS timeout triggers | Configure on-call escalation policies; produce runbooks for each alert type; train on-call team | P8 | STANDARD | Not built | §9.1 Act.6 — Go-Live / Observability
LEGEND — STATUS CODES
Simulated | Data is currently generated by simulation or random values — must be replaced with real integration
Hardcoded | Fixed value in application code — must be replaced with live data source per the lifecycle plan
Not built | Integration or feature does not yet exist — new build required
Live required | Real integration required but not yet established
One-time | One-time configuration entry; not a live integration

## Phase Gate Summary
OmniBlend — Phase Gate Summary ¦ 26-Week Implementation Lifecycle ¦ Each phase must pass ALL gate criteria before successor phase begins
Phase | Name | Weeks | Priority | Key Deliverables | Phase Gate Criteria (ALL must pass)
P1 | Infrastructure Foundation | 1–4 | PREREQUISITE | Kubernetes cluster deployed PostgreSQL RDS + TimescaleDB live Redis ElastiCache with AOF persistence SSL/HTTPS on all endpoints Dev/Staging/Production isolated | All services pass Kubernetes health checks Load test passed — API sustains target concurrent WebSocket connections SSL/HTTPS verified; HTTP→HTTPS redirect active PostgreSQL PITR tested with successful restore Auto-scaling policies validated under peak load
P2 | Security Hardening | 3–6 | PREREQUISITE | OAuth2/JWT identity provider deployed RBAC configured for 4 roles VPN tunnel to plant SCADA network API key middleware on all ingest endpoints Secrets migrated to Secrets Manager IEC 62443 Zone model implemented Immutable audit log operational Penetration test completed | All endpoints return 401 for unauthenticated requests RBAC tested — no privilege escalation possible VPN tunnel latency verified <50ms round-trip Audit log verified for batch, recipe, and quality write operations Zero secrets in source code or environment variables Penetration test signed off — zero open High/Critical findings
P3 | SCADA / OPC-UA Bridge | 5–10 | CRITICAL | OPC-UA tag audit document (all tag paths, types, polling rates) 12 tank level transmitter mappings validated vs historian 12 tank temperature sensor mappings validated vs historian Blender RPM and temperature live from VFD and thermocouple Flow meter PVs driving UI animations and batch volume totalisation SCADA alarm forwarding with <60-second latency Watchdog/heartbeat monitoring with alert configured | All 12 tank levels and 12 tank temps updating live on Tank Digital Twin Pipeline flow animations driven by real flow meter PV readings SCADA alarms in Live Event Feed within 60 seconds of activation Blender RPM and temperature matching SCADA HMI within 0.5% SCADA bridge uptime >99.5% over 7-day acceptance window Historian validation: no value deviation >0.5% vs SCADA historian over 7 days
P4 | LIMS Integration | 8–14 | CRITICAL | LIMS API mapping document with canonical payload schema Webhook or polling connector live and authenticated Predicted vs Actual delta panel active in Quality AI Engine Quality Grade A/B/C linked to incoming raw material QC Off-spec alert triggers sending hold notifications Structured LIMS archive accumulating records by batch_id On-Spec Rate % on dashboard from LIMS (not simulated) | Lab results POSTing to OmniBlend within 5 minutes of LIMS analyst sign-off Predicted vs Actual delta displayed for viscosity, flash point, TBN per batch On-Spec Rate % sourced from LIMS pass/fail — not simulated Quality Grade A/B/C from incoming raw material QC records LIMS archive accumulating structured records (target 10+ batches/week) Confidence Intervals updating based on real prediction vs actual deltas
P5 | MES / ERP Sync | 12–18 | HIGH | SAP RFC/BAPI or OData adapter deployed and authenticated Production order auto-import with 5-minute polling cycle Recipe formulations synced from ERP — 10 hardcoded seeds retired Bidirectional batch stage sync (MES ↔ OmniBlend) Material consumption actuals posting back to SAP PP-PI Timeline on Command Dashboard from real MES history Manual batch creation fallback documented and tested | Production orders auto-importing; manual creation not required for normal operations Recipe Formulations from ERP — 10 hardcoded seed recipes retired Timeline reflecting real MES production order history with timestamps Batch completion events closing MES production orders automatically Material actuals posting back to SAP PP-PI for cost settlement Error queue operational with alert on 3+ consecutive failures on same transaction
P6 | Supplier Pricing Feed | 16–20 | HIGH | Supplier pricing source mapping document EDI or API price ingestion pipeline with change detection and audit trail Recipe Lab cost-per-litre from live pricing (not hardcoded) ERP-derived lead times replacing hardcoded 2–14 day values Reliability Score from ERP on-time delivery records Cost per Batch on Command Dashboard from real procurement data Supply Optimizer producing recommendations from live data | Recipe Lab cost-per-litre (£/L) sourced from live supplier pricing feed Cost per Batch on Command Dashboard uses real material + energy costs Lead times from ERP PO history — not hardcoded 2–14 day values Reliability Scores from ERP on-time delivery records (rolling 12-month) Supply Optimizer producing actionable procurement recommendations Phase 7 ML Pipeline fully unblocked — cost data available for recipe optimiser
P7 | ML Model Training Pipeline | 18–24 | HIGH | Data extraction pipeline with quality gate (>80% field completeness) Feature engineering scripts with documented transformations Viscosity Predictor trained and validated (R² > 0.92) Flash Point Predictor trained and validated (R² > 0.92) TBN Predictor trained and validated (R² > 0.92) Off-Spec Risk Classifier (XGBoost, FN-rate < 5%) Confidence Intervals from real model performance (not fixed ±5%) AI Recipe Optimiser on live cost and quality data Drift monitoring with retraining trigger configured | All deployed regressors passed R² > 0.92 validation gate on holdout test set Off-spec classifier FN-rate < 5% on 30-batch rolling validation window Confidence Intervals derived from real model performance — fixed ±5% retired AI Recipe Suggestions running SciPy constrained optimisation on live cost and quality targets ML drift monitoring active with retraining alert at 1.5× validation MAE Model cards produced documenting training data, feature importance, and known limitations
P8 | Time-Series DB & Go-Live | 22–26 | STANDARD | Time-Series DB deployed with retention policy and capacity plan Energy Heatmap displaying 24 real BMS readings per device per day Claude API intent parsing active in AI Control Panel APM dashboards with baseline latency SLOs defined Log aggregation for all service types operational On-call configured with runbooks for all critical alert types ML drift monitoring dashboard with retraining triggers Operator training completed for all four RBAC roles Go-live completed with 4-week hypercare period | 95% of all 35 dashboard data points from live instruments, LIMS, or ERP (not simulation) SCADA bridge uptime >99.5% over 30-day acceptance window post go-live Energy Heatmap displaying 24 real BMS readings per device per day Off-spec classifier FN-rate <5% on 30 consecutive live validation batches Claude API intent parsing active — regex routing retired All penetration test findings from Phase 2 remain closed (no regression) Zero critical defects after 2-week hypercare period All eight KPI targets on track within 30 days of go-live

## Recipe Register
Indicative - OmniBlend — Recipe Register (Seed Data) ¦ Source: recipe.xlsx ¦ These 5 products are the initial hardcoded seeds to be replaced by live ERP formulations in Phase 5
Product Code | Type | Component | Description | Wt % | KV40 (mm²/s) | KV100 (mm²/s) | ASTM Method (KV) | ERP Source Required | Phase
G 40 | BO | SN 500 | SN 500 | 0.7542 | 140 | 14.4 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
G 40 | BO | BS 460 | BS 460 | 0.1692 | 140 | 14.4 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
G 40 | AD | Additives 4-5 | Additives | 0.0766 | 140 | 14.4 | — | SAP PP-PI Master Recipe (Phase 5) | P5
A 40 | BO | SN 500 | SN 500 | 0.7905 | 127 | 14 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
A 40 | BO | BS 460 | BS 460 | 0.0589 | 127 | 14 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
A 40 | AD | Additives 4-5 | Additives | 0.1506 | 127 | 14 | — | SAP PP-PI Master Recipe (Phase 5) | P5
H 20W50 SJCF | BO | HVI 120 | HVI 120 | 0.453 | 178 | 19 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
H 20W50 SJCF | AD | Additive | Additive 3 | 0.197 | 178 | 19 | — | SAP PP-PI Master Recipe (Phase 5) | P5
H 20W50 SJCF | BO | HVI 650 | HVI 650 (PulauBukom) | 0.15 | 178 | 19 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
H 20W50 SJCF | BO | GTL BO8 | GTL BO8 | 0.2 | 178 | 19 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
R 50 | BO | BS 460 | HVI 650 (PulauBukom) | 0.5 | 179 | 17 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
R 50 | BO | EHC 110 | EHC 110 (J500) XOM | 0.3697 | 179 | 17 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
R 50 | BO | GTL BO8 | XHVI 8 (Ras Laffan) | 0.0688 | 179 | 17 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
R 50 | AD | Additive | Additive | 0.0615 | 179 | 17 | — | SAP PP-PI Master Recipe (Phase 5) | P5
2T | BO | HVI 60 | HVI 60 | 0.65 | N/A | 7.5 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
2T | BO | HVI 120 | HVI 120 | 0.106 | N/A | 7.5 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
2T | BO | HVI 650 | HVI 650 | 0.13 | N/A | 7.5 | ASTM D445 | SAP PP-PI Master Recipe (Phase 5) | P5
2T | AD | Additive 3 | Additive 3 | 0.114 | N/A | 7.5 | — | SAP PP-PI Master Recipe (Phase 5) | P5
NOTE: All 5 products above (G40, A40, H 20W50 SJCF, R50, 2T) are the current hardcoded seed recipes. Phase 5 (MES/ERP Sync, Weeks 12–18) replaces all of these with live formulations synced from SAP PP-PI Master Recipe via RFC/BAPI or OData.

## KPI Tracker
OmniBlend — KPI Framework & Success Metrics ¦ Baseline captured Weeks 1–4 ¦ Reported monthly post go-live
KPI | Baseline (Current - Indicative ) | OmniBlend Target - to be set during the req discussions | Measurement Method | Phase Delivered | Priority
Batch Traceability | Partial — 3+ systems required |  | Audit test: random batch genealogy query completion time and completeness | P4 | CRITICAL
Manual Spreadsheet Use | Primary operations tool |  | Count of active production-related spreadsheets in circulation | P5 | HIGH
Shift Report Compile Time | 2–3 hours per shift |  | Time study: shift end timestamp to report distribution confirmation | P5 | HIGH
Quality Prediction Accuracy | N/A — no predictive capability |  | Monthly model performance review: RMSE and R² vs actual LIMS results | P7 | HIGH
Out-of-Spec Batch Rate | Establish baseline Weeks 1–4 |  | Monthly Quality Dashboard: OOS batches / total batches produced | P4/P7 | HIGH
Audit Readiness Time | 1–3 days to compile batch records |  | Simulated audit exercise: time to compile full batch genealogy records | P4 | CRITICAL
SCADA-to-Dashboard Latency | N/A — no live OT data in IT layer |  | Automated latency monitoring in Redis pub/sub and WebSocket layer | P3 | CRITICAL
COA Generation Time | 2–4 hours (manual compilation) |  | Timestamp: batch release event in system to COA email dispatch confirmation | P4/P8 | HIGH