SOLUTION ARCHITECTURE DOCUMENT

OmniBlend

Implementation Lifecycle

Industry 4.0 Digital Transformation for Lube Oil Blending Plants

From Data Silos to Single Source of Truth — Delivered in 6 Calendar Months

| Document Type | Product | Version | Classification |
| --- | --- | --- | --- |
| Implementation Plan | OmniBlend Platform v2.0 | v1.0 — March 2026 | CONFIDENTIAL |
| Prepared By | Approved By | Review Cycle | Distribution |
| Intelligent Manufacturing Division |  |  | Management, IT/OT, Quality — RESTRICTED |

This document defines the phased implementation lifecycle for OmniBlend — the enterprise Single Source of Truth platform for Lube Oil Blending Plants. It specifies all activities, integration requirements, responsible parties, deliverables, and phase gate criteria across an eight-phase, 26-week programme of work.

# 1. Executive Summary

OmniBlend is an enterprise-grade platform purpose-built for Lube Oil Blending Plants that resolves the fundamental Data Gap between the IT layer (ERP, financial systems, quality management) and the OT layer (SCADA, DCS, PLCs, inline analysers). This gap causes inaccurate batch costing, reactive quality control, unplanned downtime, and a dependency on manual spreadsheets that creates compliance risk and operational inefficiency.

This Implementation Lifecycle document defines eight sequential phases delivered across 26 weeks (approximately six calendar months). Each phase produces specific, verifiable deliverables and must pass a defined gate criterion before the subsequent phase proceeds. Critical-path phases are identified and flagged; the SCADA/OPC-UA bridge and LIMS integration are the two dependencies that unblock all downstream ML model training.

## 1.1 The Four Foundational Pillars

| Pillar | Description | Technology | Phase |
| --- | --- | --- | --- |
| Unified Data Architecture | Normalised PostgreSQL schema spanning batches, tanks, recipes, quality results, supply chain, and financial data. Single Source of Truth eliminating all spreadsheet reconciliation. | PostgreSQL 15+, TimescaleDB | P1 |
| Real-Time OT/IT Bridge | OPC-UA information model connected to FastAPI REST endpoints. Live SCADA data pushed into the digital twin with <2-second latency via Redis WebSocket streams. | OPC-UA, FastAPI, Redis 7 | P3 |
| AI-Powered Quality Prediction | ML models trained on 200–500 historical batches to predict viscosity, flash point and TBN before production completes. Minimum R² > 0.92 validation gate. | TensorFlow, Scikit-learn, SciPy | P7 |
| Compliance-Ready Vault | Version-controlled standards storage for IEC 62443, GAMP 5, ASTM, ISO. Instant audit-trail generation. COA auto-generated in under 5 minutes from batch release. | FastAPI, PostgreSQL, PDF engine | P8 |

## 1.2 Six-Month Timeline Overview

| Ph. | Name | Weeks | Priority | Primary Gate Criterion |
| --- | --- | --- | --- | --- |
| P1 | Infrastructure Foundation | 1–4 | PREREQUISITE | All services deployed; load test passed; SSL/HTTPS verified |
| P2 | Security Hardening | 3–6 | PREREQUISITE | All endpoints require valid JWT; RBAC tested; penetration test signed off |
| P3 | SCADA / OPC-UA Bridge | 5–10 | CRITICAL | 12 tank levels + 12 tank temps live; SCADA alarms in event feed; bridge uptime >99.5% |
| P4 | LIMS Integration | 8–14 | CRITICAL | Lab results posting ≤5 min of sign-off; Predicted vs Actual displayed per batch |
| P5 | MES / ERP Sync | 12–18 | HIGH | Production orders auto-importing; recipe formulations from ERP; MES orders auto-closing |
| P6 | Supplier Pricing Feed | 16–20 | HIGH | Real £/L pricing in Recipe Lab; lead times and reliability from ERP |
| P7 | ML Model Training Pipeline | 18–24 | HIGH | 3+ models trained on 200+ real batches; Confidence Intervals from real performance |
| P8 | Time-Series DB & Go-Live | 22–26 | STANDARD | 95% data points from live sources; SCADA uptime >99.5%; off-spec FN-rate <5% |

# 2. Phase 1 — Infrastructure Foundation

| P1 | Infrastructure Foundation Establish the production-grade hosting environment. This phase gates all others. | TIMELINE Weeks 1–4 | PRIORITY PREREQUISITE |
| --- | --- | --- | --- |

Phase 1 establishes the cloud or on-premise Kubernetes infrastructure upon which every subsequent phase depends. Docker Compose is development-only; Kubernetes or ECS is required for high-availability plant operations. No real plant data may be connected until this phase and Phase 2 (Security Hardening) are both verified and closed.

## 2.1 Activities

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | Cloud Platform Provisioning | Provision AWS EKS / Azure AKS / GCP GKE or on-premise Kubernetes for air-gapped environments. Define namespace strategy (dev/staging/production). Configure node pools and auto-scaling policies. | DevOps / Cloud Engineer |
| 2 | Reverse Proxy & CDN | Deploy Nginx or AWS ALB in front of FastAPI backend. Configure CloudFront CDN for React static asset delivery. Enforce HTTP→HTTPS redirect at proxy layer. | DevOps |
| 3 | PostgreSQL RDS Deployment | Migrate PostgreSQL 15+ to managed RDS with daily automated backups, PITR, PgBouncer connection pooling, and read replica for reporting. Test restore procedure before sign-off. | DBA / DevOps |
| 4 | TimescaleDB Extension | Enable TimescaleDB on PostgreSQL. Configure hypertable partitioning for scada_tags (1-day chunk interval). Set up continuous aggregate policies for 1-min, 15-min, and 1-hour rollups. | DBA |
| 5 | Redis ElastiCache | Deploy managed Redis 7 cluster with AOF persistence for pub/sub durability. Configure separate channels for SCADA tag streams and batch lifecycle events. Define key expiry policies. | DevOps |
| 6 | SSL / HTTPS | Provision SSL/HTTPS certificate (Let's Encrypt or commercial CA) across all /api/v1/ endpoints and React frontend. Verify certificate chain and auto-renewal process. | DevOps |
| 7 | Environment Separation | Configure dev/staging/production isolation with separate databases, Redis instances, and API keys. Staging must mirror production configuration for pre-release testing. | DevOps |
| 8 | Load Testing | Execute load test against all /api/v1/ endpoints using k6 or Locust. Validate API sustains target concurrent WebSocket connections (minimum 50 concurrent dashboard sessions). Validate auto-scaling response time. | DevOps / QA |

## 2.2 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| Kubernetes cluster running in production environment | All services pass Kubernetes health checks |
| PostgreSQL RDS with PITR verified by test restore | Load test passed — API sustains target concurrent WebSocket connections |
| TimescaleDB hypertable schema deployed and query-tested | SSL/HTTPS verified; HTTP→HTTPS redirect active |
| Redis ElastiCache running with AOF persistence verified | PostgreSQL PITR tested with successful restore |
| SSL/HTTPS on all endpoints with auto-renewal | Auto-scaling policies validated under simulated peak load |
| Dev/Staging/Production environments isolated | Phase 2 can proceed — no prerequisite gates blocked |

# 3. Phase 2 — Security Hardening

| P2 | Security Hardening Hard prerequisite. Runs in parallel with P1. No real plant data connected until all security controls verified. | TIMELINE Weeks 3–6 | PRIORITY PREREQUISITE |
| --- | --- | --- | --- |

IEC 62443 REQUIREMENT: Phase 2 implements the Zone and Conduit model partitioning the plant network into five security zones. No cross-zone connection is permitted until this model is documented, implemented, and penetration-tested.

Security hardening runs in parallel with infrastructure provisioning (Weeks 3–6). The VPN between the plant SCADA network and the cloud backend must be established and latency-tested before Phase 3 (SCADA Bridge) begins. All High and Critical findings from the internal penetration test must be remediated before Phase 3 starts.

## 3.1 IEC 62443 Zone Model

| Zone | Systems / Assets | Security Level | OmniBlend Component |
| --- | --- | --- | --- |
| Zone 0 — Process | Field instruments, sensors, actuators | SL 1: Physical security | -- |
| Zone 1 — OT/Control | DCS controllers, PLCs, SCADA servers, HMI workstations, OPC-UA servers | SL 2: Defence against unsophisticated attacker | -- |
| Zone 2 — OT/DMZ | OPC-UA proxy/gateway, data diode (critical paths), OmniBlend OT adapter microservice | SL 2–3: Conduit with deep packet inspection | OT Adapter Microservice |
| Zone 3 — IT/Application | FastAPI application server, PostgreSQL/TimescaleDB, Redis, Celery workers | SL 2: Standard IT security + network segmentation | Core Platform |
| Zone 4 — Enterprise | SAP ERP, corporate network, user workstations, external API consumers | SL 1–2: Corporate IT security, MFA enforced | Dashboard / SAP Adapter |

## 3.2 Activities

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | Identity Provider Deployment | Deploy OAuth2/JWT identity provider: Keycloak (self-hosted), Auth0, or AWS Cognito. Configure 15-minute JWT expiry, refresh token rotation, and forced logout on role change. | IT Security / DevOps |
| 2 | RBAC Configuration | Implement four-role RBAC: Operator (read + execute), Engineer (full write), Manager (read + reports), Read-Only. Map roles to specific API endpoint permissions. Test privilege escalation not possible. | IT Security |
| 3 | Plant VPN / Private Network | Establish VPN tunnel or AWS Direct Connect between plant SCADA network and cloud backend. Test tunnel latency: target <50ms round-trip. Document failover procedure. | IT/OT Engineer |
| 4 | API Key Middleware | Deploy API key authentication on all /api/v1/ingest/ endpoints. Separate key per integration system (SCADA bridge, LIMS connector, MES adapter). 90-day key rotation cycle. | IT Security |
| 5 | Secrets Management | Migrate all secrets to AWS Secrets Manager or HashiCorp Vault. Purge .env secrets from codebase, container images, and Kubernetes ConfigMaps. Verify no secrets remain in source control history. | DevOps / IT Security |
| 6 | IEC 62443 Zone Architecture | Document and implement the five-zone network model. Zone 1→Zone 2: unidirectional OPC-UA via certified industrial gateway. Zone 2→Zone 3: HTTPS/TLS 1.3 only. Direct Zone 4→Zone 1 connections architecturally prohibited. | IT/OT Engineer |
| 7 | Immutable Audit Log | Implement write-once audit log capturing: user ID, timestamp, action type, record ID, previous value, new value — for all write operations on batches, recipes, quality results, and user management. | IT Security / DevOps |
| 8 | Penetration Testing | Conduct internal penetration test against all API endpoints, authentication mechanisms, RBAC boundaries, and network segmentation. Remediate all High and Critical findings before Phase 3 begins. | IT Security / External Pen Tester |

## 3.3 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| Identity provider with JWT and refresh token rotation | All API endpoints return 401 for unauthenticated requests |
| RBAC configured for all four roles | RBAC tested — no privilege escalation possible |
| VPN tunnel to plant SCADA network established | VPN tunnel latency verified <50ms round-trip |
| API key middleware on all ingest endpoints | Audit log verified for batch creation, recipe changes, quality overrides |
| Secrets migrated — zero in codebase or containers | Zero secrets in source code or environment variables |
| IEC 62443 Zone model documented and implemented | Penetration test signed off — zero open High/Critical findings |
| Immutable audit log operational | Phase 3 (SCADA bridge) may proceed |
| Penetration test completed and High/Critical findings remediated |  |

# 4. Phase 3 — SCADA / OPC-UA Bridge

| P3 | SCADA / OPC-UA Bridge Highest-priority integration. Replaces all simulated sensor values with live OPC-UA tag data. | TIMELINE Weeks 5–10 | PRIORITY CRITICAL |
| --- | --- | --- | --- |

CRITICAL PATH: The OPC-UA bridge must be operational and accumulating SCADA historian data before Week 18 when Phase 7 (ML Training) begins. Any delay to Phase 3 proportionally delays all ML model training.

Phase 3 connects the plant OT layer to the OmniBlend digital twin via OPC-UA (IEC 62541 standard). The OPC-UA client runs as a dedicated Python microservice in Zone 3. It subscribes to monitored items on the OPC-UA server (hosted in Zone 1), receiving data change notifications rather than polling — reducing network load while ensuring data freshness.

## 4.1 Instrument Tag Register — Mandatory Fields

| Field | Type | Description | Example |
| --- | --- | --- | --- |
| tag_name | VARCHAR(30) | ISA 5.1 compliant tag designation | FIC-201 |
| instrument_type | ENUM | Flow / Temperature / Pressure / Level / Analyzer | Level |
| process_variable | VARCHAR(60) | What is being measured | Base Oil 150N level in TK-04 |
| engineering_units | VARCHAR(20) | Unit of measurement | % / m³ |
| range_low / range_high | DECIMAL(10,4) | Calibrated measurement range | 0.0 / 100.0 |
| alarm_low / alarm_high | DECIMAL(10,4) | Process alarm setpoints | 10.0 / 90.0 |
| scada_address | VARCHAR(60) | OPC-UA node ID for live data linkage | ns=2;s=Plant.TK04.LIC201.PV |
| p_and_id_ref | VARCHAR(20) | Drawing reference and revision | P&ID-003 Rev. C |
| calibration_due | DATE | Next calibration due date | 2026-09-15 |
| safety_instrumented | BOOLEAN | Part of a Safety Instrumented Function | FALSE |

## 4.2 Activities

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | Plant OPC-UA Tag Audit | Before any bridge development: document all tag paths, data types, engineering units, and polling rates. Verify all 12 tank level transmitters and 12 temperature sensors are accessible. Confirm VFD, flow meter, and weighing system tag addresses. | IT/OT Engineer + Plant Operator |
| 2 | Bridge Implementation Selection | Select OPC-UA bridge: node-opcua (Node.js), Python asyncua, or commercial Ignition Gateway. Evaluate against plant SCADA vendor compatibility and IEC 62443 certification status. | IT/OT Engineer |
| 3 | Tank Level Transmitters (×12) | Map all 12 ultrasonic/radar level transmitter OPC-UA tags → API endpoint → Fill Level % on Tank Digital Twin. Validate readings against SCADA historian for ≥7 consecutive days. | IT/OT Engineer |
| 4 | Tank Temperature Sensors (×12) | Map all 12 RTD/thermocouple tank temperature sensor tags → API endpoint → Temperature °C on Tank Digital Twin. Validate against SCADA historian. | IT/OT Engineer |
| 5 | Blender Instruments | Map blender thermocouple PV readings → Blend Simulator Temperature. Map VFD feedback signals → Mixing Speed (RPM). Validate against HMI readings. | IT/OT Engineer |
| 6 | Flow Meters | Map pipeline flow meter PV readings → animated flow visualisation + Batch Volume totalisation. Each pipeline requires a separate tag mapping. | IT/OT Engineer |
| 7 | Batch Weighing System | Map batch weighing system dosing-complete discrete signals → Progress % calculation in Blend Simulator. Requires coordination with batch control PLC program. | IT/OT Engineer + PLC Programmer |
| 8 | SCADA Alarm Forwarding | Configure discrete alarm states → POST /api/v1/ingest/events/ → Live Event Feed on Command Dashboard. Target: alarms appearing within 60 seconds of activation. | IT/OT Engineer |
| 9 | Watchdog / Heartbeat Monitor | Implement 30–60 second polling cycle with watchdog monitoring. Alert on 3 consecutive missed heartbeats. Bridge uptime target: >99.5% over 7-day acceptance window. | DevOps / IT/OT Engineer |
| 10 | SCADA Historian Validation | Validate all ingested values against SCADA historian over ≥7 days. Acceptance: no value deviation >0.5% of engineering range vs historian. | IT/OT Engineer + Quality Analyst |

## 4.3 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| OPC-UA tag audit document — all paths, types, polling rates | 12 tank levels and 12 tank temps updating live on Tank Digital Twin |
| 12 tank level transmitter mappings validated vs historian | Pipeline flow animations driven by real flow meter PV readings |
| 12 tank temperature sensor mappings validated vs historian | SCADA alarms in Live Event Feed within 60 seconds |
| Blender RPM and temperature live from VFD and thermocouple | Blender RPM and temperature matching SCADA HMI within 0.5% |
| Flow meter PVs driving UI animations and batch volume totalisation | SCADA bridge uptime >99.5% over 7-day acceptance window |
| SCADA alarm forwarding with <60-second latency | Phase 4 (LIMS) may proceed in parallel from Week 8 |
| Watchdog/heartbeat monitoring with alert configured |  |

# 5. Phase 4 — LIMS Integration

| P4 | LIMS Integration Connects real laboratory results to Quality AI Engine. Begins accumulating ML training data. | TIMELINE Weeks 8–14 | PRIORITY CRITICAL |
| --- | --- | --- | --- |

DATA ACCUMULATION: LIMS integration must be live by Week 8 to accumulate the minimum 200 batch records needed for ML model training by Week 18. This 10-week window is not recoverable if Phase 4 is delayed.

Phase 4 connects actual laboratory test results from the LIMS to OmniBlend. LIMS data, aligned by batch_id, is the primary training dataset for all ML models in Phase 7. The integration also activates the Predicted vs Actual comparison panel, provides the Quality Grade signal for the Supply Optimizer, and powers the On-Spec Rate % KPI on the Command Dashboard.

## 5.1 Quality Parameters Tracked

| Parameter | ASTM Method | Target | ML Model (P7) |
| --- | --- | --- | --- |
| Kinematic Viscosity @ 40°C | ASTM D445 | Product-specific (cSt) | Viscosity Predictor |
| Kinematic Viscosity @ 100°C | ASTM D445 | Product-specific (cSt) | Viscosity Predictor |
| Flash Point (Cleveland OC) | ASTM D92 | Product-specific (°C) | Flash Point Predictor |
| Total Base Number (TBN) | ASTM D2896 | Product-specific (mg KOH/g) | TBN Predictor |
| Total Acid Number (TAN) | ASTM D664 | Product-specific (mg KOH/g) | -- |
| Density | ASTM D4052 | Product-specific (kg/L) | -- |
| Pour Point | ASTM D97 | Product-specific (°C) | -- |
| Pass / Fail Disposition | QC Plan | All parameters in spec | Off-Spec Classifier |

## 5.2 Activities

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | LIMS Vendor API Mapping | Map LIMS vendor API (LabVantage / STARLIMS / custom) to POST /api/v1/quality/lab-results. Define canonical payload schema: batch_id, sample_time, parameter, method, value, units, pass_fail, analyst_id. | IT/OT Engineer + LIMS Vendor |
| 2 | Webhook / Polling Connector | Implement webhook (preferred) or polling connector. Webhook triggers on instrument sign-off in LIMS — the event confirming analyst review and approval. Target: results posting within 5 minutes of sign-off. | IT/OT Engineer |
| 3 | Predicted vs Actual Panel | Activate the Predicted vs Actual comparison panel in the Quality AI Engine. Display delta between formula-based predictions and actual LIMS results per batch. Drives confidence interval calculations in Phase 7. | Development Team |
| 4 | Confidence Interval Derivation | Begin deriving real confidence intervals from prediction vs actual deltas, replacing the fixed ±5% placeholder. CI narrows as batch records accumulate. | Data Scientist |
| 5 | Quality Grade Linkage | Link incoming raw material QC inspection results from LIMS to Quality Grade (A/B/C) in the Supply & Cost Optimizer. A = meets all specification limits; B = acceptable with caveats; C = conditional use only. | Quality Analyst + IT/OT Engineer |
| 6 | Off-Spec Alert Triggers | Configure automated off-spec alerts: LIMS pass/fail disposition → batch hold notification → Live Event Feed. Operator must acknowledge hold before batch release. | Quality Analyst + Development |
| 7 | Structured LIMS Data Archiving | Configure LIMS result archiving aligned by batch_id and timestamp. Archive schema must include: ingredient percentages, process temperatures, RPM profiles, and final quality results for ML feature engineering. | DBA + Data Scientist |
| 8 | On-Spec Rate KPI Activation | Activate On-Spec Rate % on the Command Dashboard, sourced from LIMS pass/fail results only — not simulation. | Development Team |

## 5.3 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| LIMS API mapping document with payload schema | Lab results POSTing within 5 minutes of LIMS sign-off |
| Webhook or polling connector live and authenticated | Predicted vs Actual delta displayed for viscosity, flash point, TBN |
| Predicted vs Actual delta panel active in Quality AI Engine | On-Spec Rate % sourced from LIMS pass/fail — not simulated |
| Quality Grade A/B/C linked to incoming raw material QC | Quality Grade A/B/C from incoming raw material QC records |
| Off-spec alert triggers sending hold notifications | LIMS archive accumulating structured records (target 10+ batches/week) |
| Structured LIMS archive accumulating records by batch_id | Confidence Intervals updating based on real deltas |
| On-Spec Rate % on dashboard from LIMS (not simulated) |  |

# 6. Phase 5 — MES / ERP Sync

| P5 | MES / ERP Sync Automates the production order lifecycle and replaces hardcoded seed recipes with live ERP formulations. | TIMELINE Weeks 12–18 | PRIORITY HIGH |
| --- | --- | --- | --- |

Phase 5 connects OmniBlend to SAP PP-PI, Oracle Manufacturing, or a custom MES. The primary outcomes are: (1) production orders auto-import to create batches without manual entry, (2) recipe formulations sync from ERP replacing the 10 hardcoded seed recipes, and (3) batch completion events close MES production orders automatically. A manual fallback for batch creation must be designed and tested in case MES API access is restricted by IT governance.

## 6.1 SAP Module Integration Matrix

| SAP Module | Flow | OmniBlend Function | Integration Method |
| --- | --- | --- | --- |
| PP-PI | Bidirectional | Production orders drive batch creation. Actual quantities consumed written back for cost settlement. | RFC/BAPI (CO11N) or PP OData (S/4HANA) |
| MM | Inbound | Goods receipts trigger material master updates; inventory and specs kept synchronised. | BAPI_GOODSMVT_CREATE or MM OData |
| QM | Bidirectional | Inspection lots linked to OmniBlend LIMS results. Pass/fail decisions drive QM usage decisions enabling or blocking goods issue. | BAPI_QMEL_CREATE, QM OData |
| PM | Inbound | Equipment master data and maintenance history imported to populate instrument registers and maintenance calendars. | BAPI_EQUI_GETLIST, IE03 OData |
| FI/CO | Outbound | Batch cost data (material + energy + rework) aggregated and exported to CO-PC for profitability analysis. | CO-PC settlement via KB21N or CO OData |
| SD | Inbound | Customer quality specifications from sales orders loaded into batch quality plan. | BAPI_SALESORDER_GETLIST, SD OData |

## 6.2 Activities

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | MES/ERP API Connection | Establish API connection to SAP PP via RFC/BAPI adapter (pyrfc) or OData REST for S/4HANA. Authenticate via service account with minimum required SAP authorisation objects. | IT/OT Engineer + SAP Basis |
| 2 | Production Order Auto-Import | On release of a production order in SAP PP-PI, auto-create a corresponding blend batch in OmniBlend with recipe, target quantity, and customer spec. Polling interval: 5 minutes. | IT/OT Engineer + Development |
| 3 | Recipe Formulations Sync | Sync recipe formulations from ERP product codes. Replace 10 hardcoded seed recipes with live ERP data. OmniBlend recipe version must match SAP recipe version. | Blend Technologist + IT/OT Engineer |
| 4 | Bidirectional Batch Stage Sync | MES order status drives OmniBlend batch status (Released → In Progress → Completed). OmniBlend batch completion triggers MES production order close (CO15 confirmation). | IT/OT Engineer |
| 5 | Material Consumption Postback | Post material actuals back to ERP on batch close: SAP material number, planned quantity, actual quantity, UoM. This drives PP-PI cost settlement and profitability reporting. | IT/OT Engineer + SAP Consultant |
| 6 | Timeline Sync | Sync production order status history from MES to power the Timeline on the Command Dashboard. Each stage transition must carry a timestamp. | IT/OT Engineer |
| 7 | Manual Fallback Design | Design and test manual batch creation fallback for restricted MES API access scenarios. Must capture all required fields: recipe, target quantity, planned start date, operator. | Development + Quality Analyst |
| 8 | Error Handling & Retry Queue | Implement dedicated error queue for failed SAP transactions with full payload logging. Alert triggered after 3 consecutive failures on same transaction type. | IT/OT Engineer + DevOps |

## 6.3 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| SAP RFC/BAPI or OData adapter deployed and authenticated | Production orders auto-importing; manual batch creation not required for normal operations |
| Production order auto-import with 5-minute polling | Recipe Formulations from ERP — 10 hardcoded seed recipes retired |
| Recipe formulations synced from ERP — hardcoded seeds retired | Timeline reflecting real MES production history |
| Bidirectional batch stage sync operational | Batch completion closing MES production orders automatically |
| Material consumption actuals posting back to SAP PP-PI | Material actuals posting back to SAP PP-PI for cost settlement |
| Timeline on Command Dashboard from real MES history | Error queue operational with alert on 3+ consecutive failures |
| Manual batch creation fallback documented and tested |  |

# 7. Phase 6 — Supplier Pricing Feed

| P6 | Supplier Pricing Feed Replaces all hardcoded pricing with live contract data. Enables real £/L cost optimisation. | TIMELINE Weeks 16–20 | PRIORITY HIGH |
| --- | --- | --- | --- |

Phase 6 replaces all hardcoded unit costs in the Recipe Lab and Supply & Cost Optimizer with live supplier pricing data. It also replaces hardcoded lead times (2–14 days) and reliability scores (0.75–0.99) with ERP-derived actuals. The outcome is a Recipe Lab that produces accurate cost-per-litre calculations and a Supply Optimizer that generates actionable procurement recommendations based on real, current data.

## 7.1 Activities

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | Supplier Pricing Source Identification | Identify and onboard EDI price list feeds or supplier portal REST APIs per raw material supplier. Map supplier codes and material codes between external pricing feeds and OmniBlend material master (SAP material number). | Procurement + IT/OT Engineer |
| 2 | Price Ingestion Pipeline | Implement scheduled price ingestion with change detection and audit trail. Price updates stored with effective date and expiry date. Ingestion frequency: daily for EDI, real-time webhooks where available. | IT/OT Engineer |
| 3 | Recipe Lab Cost Replacement | Replace hardcoded £/L unit costs in Recipe Lab with live EDI values. Cost per Litre must account for: base material cost, ERP-validated freight, import duties, and wastage factors. Display cost breakdown per component. | Development + Procurement |
| 4 | ERP Lead Time Integration | Extract historical PO-to-delivery performance from SAP MM (ME2M or equivalent). Calculate average lead time per supplier per material. Replace hardcoded 2–14 day values. | IT/OT Engineer + SAP Consultant |
| 5 | Reliability Score Calculation | Calculate Reliability Score from ERP on-time delivery records: on-time deliveries / total deliveries over rolling 12-month window per supplier. Replace hardcoded 0.75–0.99 values. Recalculate monthly. | IT/OT Engineer + Data Analyst |
| 6 | Cost per Batch on Dashboard | Activate real Cost per Batch (£/L) on Command Dashboard: (component actuals × live unit costs) + energy usage × kWh rate + packaging cost. Validate against actual procurement cost reports. | Development + Finance |
| 7 | Supply Optimizer Connection | Connect live pricing, lead time, and reliability data to the Supply & Cost Optimizer. Enable constrained procurement optimisation: minimum cost subject to lead time ≤ X days and reliability ≥ Y. | Data Scientist + Development |

## 7.2 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| Supplier pricing source mapping document | Recipe Lab cost-per-litre (£/L) sourced from live supplier pricing |
| EDI or API price ingestion pipeline with change detection | Cost per Batch uses real material + energy costs |
| Recipe Lab cost-per-litre from live pricing (not hardcoded) | Lead times from ERP PO history — not hardcoded |
| ERP-derived lead times replacing hardcoded values | Reliability Scores from ERP on-time delivery records |
| Reliability Score from ERP on-time delivery history | Supply Optimizer producing actionable procurement recommendations |
| Cost per Batch on Command Dashboard from real procurement data | Phase 7 (ML Pipeline) fully unblocked — cost data available for recipe optimiser |
| Supply Optimizer producing recommendations from live data |  |

# 8. Phase 7 — ML Model Training Pipeline

| P7 | ML Model Training Pipeline Replaces all formula-based predictors with trained, validated ML models. | TIMELINE Weeks 18–24 | PRIORITY HIGH |
| --- | --- | --- | --- |

DATA DEPENDENCY: Phase 7 requires minimum 200 completed LIMS batch records (from Phase 4) aligned with SCADA historian data (from Phase 3). The Off-Spec Risk Classifier requires 500+ batches. If fewer records are available by Week 18, physics-informed hybrid models are used as interim deployment.

Phase 7 is the AI core of OmniBlend. All models are loaded into existing FastAPI inference wrappers without API changes — the wrapper interface is stable from Phase 1. Every model must pass a minimum validation gate (R² > 0.92 for regressors, FN-rate < 5% for the off-spec classifier) before deployment to the production inference endpoint.

## 8.1 Model Specifications

| Model | Algorithm | Min Batches | Validation Gate | Key Input Features |
| --- | --- | --- | --- | --- |
| Viscosity Predictor | GradientBoosting + Refutas index | 200+ | R² > 0.92, MAE < 2 cSt | Ingredient %, blend temp, RPM profiles |
| Flash Point Predictor | Neural Network (2-layer, 64 nodes, ReLU) | 200+ | R² > 0.92, MAE < 3°C | Base oil flash, additive contribs, tank history |
| TBN Predictor | RandomForest Regressor | 200+ | R² > 0.92 | Additive concentrations, blend conditions |
| Off-Spec Risk Classifier | XGBoost Classifier | 500+ | FN-rate < 5% on 30-batch validation | All process params + LIMS pass/fail labels |
| Confidence Intervals | Bootstrap from model residuals | 200+ | Real CI replaces fixed ±5% | Derived from prediction vs actual deltas |
| AI Recipe Optimiser | SciPy constrained optimisation (SLSQP) | N/A | Solution within 0.5% of spec limits | Real cost (P6) + quality targets (P4/P7) |

## 8.2 Training Pipeline Steps

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | Data Extraction | Pull historical batch records from LIMS archive and SCADA historian, aligned by batch_id and timestamp. Apply data quality gate: records failing >80% field completeness quarantined before inclusion. | Data Scientist |
| 2 | Feature Engineering | Normalise ingredient percentages (sum = 100%). Encode blend temperature profiles (mean, max, gradient, rate of rise). Encode RPM profiles (mean, variance). Derive mixing energy feature = RPM × time × torque proxy. One-hot encode product family. | Data Scientist |
| 3 | Viscosity Model Training | Train Viscosity Predictor using GradientBoostingRegressor on ingredient % + process features → actual LIMS viscosity. Compare against Refutas deterministic baseline. 80/20 train/test split with cross-validation hyperparameter tuning. | Data Scientist |
| 4 | Flash Point Model Training | Train Flash Point Predictor using 2-layer neural network (64 nodes, ReLU). Flash point is sensitive to trace contamination — include tank history as a feature to capture carryover effects. | Data Scientist |
| 5 | TBN & Off-Spec Training | Train TBN Predictor (RandomForest) on additive concentration features. Train Off-Spec Risk Classifier (XGBoost) on combined process + quality features with LIMS pass/fail label. Evaluate classifier: precision, recall, and critically false-negative rate. | Data Scientist |
| 6 | Validation & MLOps Gate | Evaluate all regressors on holdout test set: R² > 0.92 required for deployment. Evaluate classifier on 30-batch rolling validation window: FN-rate < 5%. Generate model card documenting training data summary, feature importance, known limitations. | Data Scientist + Quality Manager |
| 7 | Model Serialisation | Serialise via joblib (.pkl) or TF SavedModel. Load into existing FastAPI ML inference wrappers — no API code changes required. Deploy to staging, validate predictions match training notebook output, then promote to production. | DevOps + Data Scientist |
| 8 | AI Recipe Optimiser | Implement AI Recipe Suggestions using SciPy constrained optimisation (SLSQP method). Objective: minimise cost (£/L). Constraints: viscosity target ± tolerance, flash point ≥ minimum, TBN within range, ingredient sum = 100%. User-definable cost/quality weight slider. | Data Scientist + Development |
| 9 | Drift Monitoring Setup | Configure drift monitoring: track MAE between model predictions and LIMS actuals weekly. Trigger retraining alert when MAE exceeds 1.5× the validation MAE. Document retraining procedure. | Data Scientist + DevOps |

## 8.3 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| Data extraction pipeline with quality gate (>80% completeness) | All deployed models passed R² > 0.92 gate (regressors) |
| Feature engineering scripts with documented transformations | Off-spec classifier FN-rate < 5% on 30-batch validation window |
| Viscosity Predictor trained and validated (R² > 0.92) | Confidence Intervals derived from real model performance (not fixed ±5%) |
| Flash Point Predictor trained and validated (R² > 0.92) | AI Recipe Suggestions running constrained optimisation on live data |
| TBN Predictor trained and validated | Drift monitoring active with documented retraining procedure |
| Off-Spec Risk Classifier with FN-rate < 5% | Phase 8 (Observability & Go-Live) may proceed |
| Confidence Intervals from real model performance |  |
| AI Recipe Optimiser on live cost and quality data |  |
| Drift monitoring with retraining trigger configured |  |

# 9. Phase 8 — Time-Series DB, Observability & Go-Live

| P8 | Time-Series DB & Go-Live Completes observability stack, activates Energy Heatmap, and manages the operational go-live. | TIMELINE Weeks 22–26 | PRIORITY STANDARD |
| --- | --- | --- | --- |

ENERGY HEATMAP NOTE: The Energy Heatmap requires 24 time-series readings per equipment device per day from BMS APIs. This makes the Time-Series DB a functional requirement — without it, the Energy Heatmap cannot be populated.

Phase 8 completes the observability stack (APM, log aggregation, on-call), deploys the Energy Heatmap, activates the Claude API for the AI Control Panel NLP, and manages the phased go-live. The 4-week hypercare period (Weeks 23–26) provides intensive support during the transition from simulation to fully live operations.

## 9.1 Activities

| # | Activity | Detail & Integration | Owner / System |
| --- | --- | --- | --- |
| 1 | Time-Series DB Deployment | Deploy InfluxDB or TimescaleDB with 30-second sensor reading retention. Define data retention tiers: full resolution (30-day), 1-min aggregates (1-year), hourly aggregates (5-year). Capacity plan: 24 readings/device/day × device count × retention window. | DBA / DevOps |
| 2 | Energy Heatmap Ingestion | Implement 24 time-series readings per equipment device per day from BMS APIs. Map BMS device IDs to OmniBlend equipment register. Display on Command Dashboard as hourly heat grid by device. | IT/OT Engineer + BMS Vendor |
| 3 | Claude API — AI Control Panel | Activate Claude API (Anthropic REST API, api.anthropic.com) as NLP intent parser for the AI Control Panel. Replace regex/keyword routing. Map natural language commands to real internal API endpoints. Implement caching, fallback routing on timeout, and graceful degradation. | Development Team |
| 4 | APM & Monitoring | Deploy Datadog, Prometheus+Grafana, or equivalent. Monitor: API latency (p50, p95, p99), error rates per endpoint, WebSocket connection count and lag, PostgreSQL query times, Redis pub/sub message rate, SCADA bridge heartbeat. | DevOps |
| 5 | Log Aggregation | Deploy ELK Stack or AWS CloudWatch. Configure log ingestion for: application errors, security audit trail, SCADA bridge connectivity events, LIMS connector activity, SAP integration errors. | DevOps |
| 6 | On-Call Configuration | Configure PagerDuty or OpsGenie with escalation policies. Alert triggers: API health check failure, PostgreSQL connection pool exhaustion, Redis pub/sub failure, SCADA bridge heartbeat miss (3 consecutive), LIMS connector timeout (>15 minutes). Runbooks for each alert type. | DevOps + IT/OT Engineer |
| 7 | ML Drift Monitoring Dashboard | Build drift monitoring dashboard: prediction vs LIMS actual MAE per model per week for all deployed models. Configure retraining trigger at 1.5× validation MAE. | Data Scientist + Development |
| 8 | Operator Training | Deliver role-based training for all four RBAC roles: Operator (batch execution, live dashboard), Engineer (recipe management, instrument registers), Manager (reporting, KPI dashboards), Read-Only (external stakeholders). Quick reference cards produced for each role. | Training Coordinator + All Discipline Leads |
| 9 | Go-Live Transition & Hypercare | Execute phased go-live: simulated data sources switched off sequentially as each live integration is verified. Four-week hypercare period with dedicated on-site support. Zero critical defects target after 2-week hypercare. | All Teams |
| 10 | Capacity Planning | Finalise time-series DB capacity plan: 24 readings/device/day × number of devices × retention window in years. Document storage growth projections for 1-year and 3-year horizons. | DBA + DevOps |

## 9.2 Deliverables & Gate Criteria

| KEY DELIVERABLES | PHASE GATE CRITERIA |
| --- | --- |
| Time-Series DB with retention policy and capacity plan | 95% of all 35 data points from live instruments, LIMS, or ERP |
| Energy Heatmap displaying 24 real BMS readings/device/day | SCADA bridge uptime >99.5% over 30-day acceptance window |
| Claude API intent parsing active in AI Control Panel | Energy Heatmap displaying 24 real BMS readings per device per day |
| APM dashboards with baseline latency SLOs defined | Off-spec classifier FN-rate <5% on 30 consecutive live validation batches |
| Log aggregation for all service types operational | Claude API intent parsing active — regex routing retired |
| On-call configured with runbooks for all critical alert types | All penetration test findings from Phase 2 remain closed |
| ML drift monitoring dashboard with retraining triggers | Zero critical defects after 2-week hypercare period |
| Operator training completed for all four RBAC roles | All eight KPI targets from Section 10 on track within 30 days of go-live |
| Go-live completed with 4-week hypercare period |  |
| KPI baseline measurements captured |  |

# 10. KPI Framework & Success Metrics

OmniBlend success is measured against eight Key Performance Indicators spanning operational efficiency, quality performance, compliance readiness, and financial impact. Baseline measurements are captured during Weeks 1–4 and reported monthly post-go-live.

| KPI | Baseline | OmniBlend Target | Measurement Method |
| --- | --- | --- | --- |
| Batch Traceability | Partial — 3+ systems | 100% — single-query genealogy | Audit test: random batch genealogy query completion time |
| Manual Spreadsheet Use | Primary operations tool | Zero — all data in OmniBlend or SAP | Count of active production-related spreadsheets |
| Shift Report Compile Time | 2–3 hours per shift | < 15 minutes (auto-generated) | Time study: shift end to report distribution |
| Quality Prediction Accuracy | N/A — no capability | R² > 0.92, > 95% confidence interval | Monthly model performance review: RMSE and R² vs actuals |
| Out-of-Spec Batch Rate | Establish baseline P1 | 15% reduction within 6 months | Monthly dashboard: OOS batches / total batches |
| Audit Readiness Time | 1–3 days to compile | < 2 hours (automated vault query) | Simulated audit: time to compile full batch records |
| SCADA-to-Dashboard Latency | N/A — no live OT/IT | < 2 seconds end-to-end | Automated latency monitoring in Redis/WebSocket layer |
| COA Generation Time | 2–4 hours (manual) | < 5 minutes (automated) | Timestamp: batch release event to COA email dispatch |

# 11. Risk Register

The following risks are identified across the eight-phase programme. Risks are reviewed at each phase gate. Likelihood and impact ratings: High / Medium / Low / Critical.

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| OPC-UA tag mapping differs from expected plant structure — tag paths or data types do not match documentation | High | High | Conduct plant OPC-UA tag audit before bridge development. Allow 2-week buffer for discrepancy resolution in Phase 3 schedule. |
| Insufficient LIMS historical data for ML training — fewer than 200 completed batch records available by Week 18 | Medium | High | Supplement with physics-informed hybrid models during accumulation. Begin LIMS archiving from Phase 4 Week 8. Track batch count weekly. |
| VPN latency exceeds 60-second SCADA data staleness threshold | Medium | Medium | Deploy OPC-UA bridge on plant-side edge server; only aggregated payloads traverse VPN. Monitor latency in Phase 2 before Phase 3 begins. |
| MES/ERP API access restricted by IT governance — SAP RFC or OData access denied | Medium | High | Engage IT and ERP vendor at Phase 5 Week 12 kick-off. Design manual batch creation fallback. Escalate to Plant Manager if API access not granted by Week 14. |
| Security hardening delays go-live — penetration test findings not remediated on schedule | Low | Critical | Begin security sprint in Week 3 in parallel with P1. P2 must not slip past Week 6. Engage external pen tester by Week 4 to avoid booking delays. |
| Claude API latency or quota limits affect AI Control Panel user experience | Medium | Medium | Implement request caching for common command patterns. Fallback to keyword routing on timeout. Monitor quota usage from go-live. |
| Energy Heatmap BMS API unavailable or non-standard — 24 readings/device/day cannot be achieved | Medium | Medium | Engage BMS vendor in Phase 8 Week 22. Identify alternative data path. Fall back to daily energy totals if sub-daily readings are unavailable. |
| Poor-quality historical batch records degrade ML model accuracy | Medium | High | Run data quality assessment during Phase 4. Brief plant operators on record completeness requirements. Quality Manager mandates completeness from Phase 4 onwards. |

# 12. Integration Contact Matrix

Named technical and business contacts must be confirmed before each phase begins. All integration vendors require confirmed API access before the phase kick-off meeting.

| System | Vendor / Team | Technical Contact | Integration Type | Phase |
| --- | --- | --- | --- | --- |
| SCADA / DCS | TBD | TBD | OPC-UA → REST Bridge (asyncua / Ignition / node-opcua) | P3 (Weeks 5–10) |
| LIMS | TBD | TBD | REST API / Webhook (LabVantage / STARLIMS / custom) | P4 (Weeks 8–14) |
| MES / ERP (SAP) | TBD / SAP Basis | TBD | RFC/BAPI adapter or OData REST (S/4HANA) | P5 (Weeks 12–18) |
| Supplier Pricing | TBD | TBD | EDI price lists or Supplier Portal REST API | P6 (Weeks 16–20) |
| Smart Meters (BMS) | TBD / BMS Vendor | TBD | BMS REST API — 24 readings/device/day | P8 (Weeks 22–26) |
| Claude API (NLP) | Anthropic | api.anthropic.com | Anthropic REST API — NLP intent parsing for AI Control Panel | P8 (Weeks 22–26) |

# 13. Document Control

| Version | Date | Change Summary |
| --- | --- | --- |
| 1.0 | March 2026 | Initial Implementation Lifecycle document — all 8 phases, integration contact matrix, risk register, KPI framework. |

| Field | Detail |
| --- | --- |
| Document Owner | Plant Manager / Digital Transformation Lead |
| Technical Author | OmniBlend Platform Architect |
| Review Cycle | At each phase gate, or upon any major scope change |
| Distribution | Plant Management, Quality, IT/OT, SAP Business Owner — RESTRICTED |
| Storage Location | OmniBlend Document Vault — Compliance & Governance section |

ANNEX A — DOCUMENT ASSISTANT MODULE (D0–D6 RAG)

NOTE: This module is fully built in the current simulator but is absent from the main Implementation Lifecycle plan above. It is an additional capability delivered as part of the simulator shell and is documented here for completeness and traceability.

A.1  Module Overview

The Document Assistant is an eighth simulator module providing Retrieval-Augmented Generation (RAG) search across seven internal OmniBlend knowledge-base documents (D0–D6). It enables operators and engineers to query technical standards, batch records, SCADA tag registers, cybersecurity assessments, process maps, QC procedures, and LIMS specifications using natural language, with answers generated by an Ollama LLM and attributed to specific source documents.

Implementation: DocumentAssistantPage.tsx (624 lines) | Backend: document_rag.py | State: docAssistantStore (Zustand) | APIs: /api/v1/ai/doc-query, /api/v1/ai/doc-status, /api/v1/ai/doc-content/{doc_id}

A.2  Technology Stack

| Component | Role |
| --- | --- |
| Ollama LLM | Local language model; synthesises retrieved passages into coherent answers |
| Sentence-Transformer Embeddings | Converts query and document chunks into vectors for similarity ranking |
| Vector Store (in-memory) | Cosine similarity over chunk embeddings; returns top-K passages to LLM |
| FastAPI (/api/v1/ai/) | doc-query (POST), doc-status (GET), doc-content/{id} (GET) |
| Zustand docAssistantStore | Chat messages, document content, last cited sources, typing animation state |
| DocumentAssistantPage.tsx | Tabbed UI: Quick Prompts tab (44 prompts) + Document Reader tab; 624 lines |

A.3  Knowledge Base (D0–D6)

| ID | Document | Key Content |
| --- | --- | --- |
| D0 | RAG Demo Guide | 88 sample questions across all six LOBP domains |
| D1 | Batch Manufacturing Record | 15W-40 formula, QC results, Certificate of Analysis fields |
| D2 | SCADA / OPC-UA Tag Register | 12-tag table, SAP integration mapping, alarm thresholds |
| D3 | Cybersecurity Risk Assessment | IEC 62443 zone model, risk register, control recommendations |
| D4 | As-Is / To-Be Process Map | 3 process areas, KPI impact analysis, gap summary |
| D5 | QC Test Procedures & Specifications | 6-grade spec matrix (viscosity, flash, TBN), 3 SOPs |
| D6 | LIMS Requirements Specification | 12 functional requirements, 5-instrument integration matrix |

A.4  Features Built

| Data Point | Phase | Priority | Status | Integration Method / Logic |
| --- | --- | --- | --- | --- |
| RAG Document Search (7 docs) | — | BUILT | Built (Simulator) | query → embedding → cosine similarity → top-K retrieval → Ollama synthesis → source-attributed response via POST /api/v1/ai/doc-query |
| Quick Prompts Library (44 prompts) | — | BUILT | Built (Simulator) | 44 pre-loaded prompts grouped by D0–D6 document; domain-specific (LOBP ops, SCADA, QC, cybersecurity, LIMS, process mapping) |
| AI Response with Source Attribution | — | BUILT | Built (Simulator) | Real-time typing animation; cited source documents rendered as named document cards with title and section reference per response |
| Knowledge Base Status Tracker | — | BUILT | Built (Simulator) | GET /api/v1/ai/doc-status: per-document chunk count & embedding status; displayed as live status panel in UI |

A.5  Alignment with Existing Lifecycle Phases

The Document Assistant pre-delivers elements of two lifecycle deliverables that are formally scoped in Phase 8:

Claude API (P8, §9.1 Act.3):  Current: Ollama local LLM. Phase 8 upgrade path: replace Ollama with Claude API (api.anthropic.com) for higher-quality synthesis and streaming responses.

Compliance-Ready Vault (P8 Pillar):  The Document Assistant can serve as the front-end for the IEC 62443 / GAMP 5 / ASTM / ISO standards library referenced in the Compliance-Ready Vault foundational pillar, subject to expanding the D0–D6 corpus to include those standards.

LIMS Integration (P4):  Ingest signed-off LIMS batch reports into D1/D5; auto-reindex on LIMS webhook, enabling queries against real batch quality results.

MES / ERP Sync (P5):  Pull live SAP PP-PI master recipes into D1 knowledge base; retire static seed document when ERP sync is operational.

CONFIDENTIAL — FOR INTERNAL USE ONLY  |  OmniBlend Platform v2.0  |  Intelligent Manufacturing Division